## OE Tracker Jan - Dec 2026
S.No | OE Renewal Doc Receive/ Received Date | Client | CRM | Config Analyst | OE Type | Sort By OE Start Date -1 Blackout | OE End Date (EE) | OE End Date (HR) | OE Effective | Type of OE | Plans with Active OE | Plans with Passive OE | OE Setup Status | Review/Testing Status | Finalization Rules Status | Announcement Email to be Sent By | Reminder Emails Frequency | OE Closure | OE Finalization Date | HGS Comments
1 | 2026-02-18 | W.T.Rich | Nitya | Pratyush | Full | 2026-03-04 | 2026-03-13 | 2026-03-13 | 2026-04-01 | Active+Passive | FSA and 401(k) | All Plans | Completed | Completed | Received | Configuration Team |  | Completed | 2026-03-16 | Medical plan rates changes. DO NOT SEND EMAILS to Union Ees
2 |  | Fiore and Sons Inc. | Juan | Vamsi | Full |  |  |  | 2026-05-01
3 | 2026-03-25 | Stratus Systems LLC | Nitya | Jeevan | Full | 4/06/2026 | 2026-04-20 | 2026-04-20 | 2026-05-01 | Active | All Plans | N/A | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-04-21 | Medical We have renamed the existing plans - MTBCB014 PPO to MTBCB514 PPO - MTBEE026 HMO to MTBEE526 HMO Dental Rate changes Voluntary Life GI Rules changes New Plans added - Short-Term Disability - (Principal) HSA - (Flores) Hospital Indemnity - (Principal) Accident - (Principal) Criticall Illness - (Principal) Plan Terminated - HSA - (Aflac) Aflac Group Accident Insurance - (Aflac) Aflac Group Critical Illness Insurance - (Aflac) Aflac Group Voluntary Short-Term Disability - (Aflac) Reminder - 4/7, 4/9,4/11, 4/13, 4/14, 4/15, 4/16, 4/17, 4/18, 4/19, 4/20
4 | 2026-04-07 | Howard Sheppard LLC | Juan | Vamsi | Full | 2026-04-20 | 2026-05-01 | 2026-05-01 | 2026-06-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-05-04 | Rate Changes for Medical Plans Blue Open Access POS - Smoker Blue Open Access POS - Non-Smoker Plan Termination - Whole Life - Grandfathered Reminder - 4/23, 4/26, 4/29, and 4/30
5 | 2026-04-25 | Evans Contracting Group | Nitya | Vamsi | Full | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-06-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2026-05-12 | Rate changes for Medical and Dental Plans Reminder Emails - 5/5,5/6,5/7,5/8,5/9,5/10,5/11
6 | 2026-04-10 | K2 Construction | Nitya | Jeevan | Full | 2026-05-04 | 2026-05-20 | 2026-05-20 | 2026-06-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-05-22 | Medical Carrier Change from BlueCross BlueShield Nebraska to Medica Medical New Plan - Medica National $2500 - Outside Lincoln/Omaha - Medica National $4000 - Outside Lincoln/Omaha - Medica National $7000 - Outside Lincoln/Omaha - Medica National $2500 - Medica National $4000 - Medica National $7000 - Medica Elevate $2500 - Medica Elevate $4000 - Medica Elevate $7000 - Medica CHI $2500 - Medica CHI $4000 - Medica CHI $7000 Medical Plans Terminated - Medical: NB BlueFreedom Option 39 Rx Option 6 NR - Outside Lincoln/Omaha - Medical: NB: BlueFreedom Option 69 Rx Option 6 NR - Outside Lincoln/Omaha - Medical: NB BlueFreedom HSA Option 66 NR - Outside Lincoln/Omaha - Medical: NB BlueFreedom Option 39 Rx Option 6 NR - Medical: PSBC BlueFreedom Option 39 Rx Option 6 NR - Medical: BH BlueFreedom Option 39 Rx Option 6 NR - Medical: NB: BlueFreedom Option 69 Rx Option 6 NR - Medical: PSBC BlueFreedom Option 69 Rx Option 6 NR - Medical: BH BlueFreedom Option 69 Rx Option 6 NR - Medical: NB BlueFreedom HSA Option 66 NR - Medical: PSBC BlueFreedom HSA Option 66 NR - Medical: BH BlueFreedom HSA Option 66 NR Reminder - 5/8, 5/13, 5/19 at (8am EST)
7 | 2026-04-25 | Quest Building Corp | Nitya | Jeevan | Full | 2026-05-01 | 2026-05-22 | 2026-05-22 | 2026-06-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-05-26 | Basic Life Rate changes Reminder Emails - 5/1, 5/8, 5/15, 5/18, 5/19, 5/20, 5/21, 5/22.
8 | 2026-04-29 | Colite Technologies | Nitya | Jeevan | Full | 2026-05-06 | 2026-05-14 | 2026-05-14 | 2026-06-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2026-05-15 | Rate Changes Medical New Plan HSA Reminder Emails - 5/6, 5/7, 5/8, 5/9, 5/10, 5/11, 5/12, 5/13, 5/14.
9 | 2025-04-20 | Iowa City Community School District | Juan | Pratyush | Full | 2026-05-01 | 2026-05-31 | 2026-05-31 | 2026-07-01 | Active+Passive | FSA Plans | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-06-02 | No Rate change received Reminder Emails - Every Other Days
10 |  | SPC Mechanical | Nitya | Jeevan | Full |  |  |  | 2026-07-01
11 |  | AC Systems | Nitya |  | Full |  |  |  | 2026-07-01
12 | 2026-06-23 | Monks Painting | Nitya | Vamsi | Full | 2026-06-23 | 2026-06-30 | 2026-06-30 | 2026-07-01 | Passive | N/A | All Plans | Completed | Completed |  | Configuration Team |  | Completed | 2026-07-01 | New Client Going with OE
13 | 2026-07-01 | Hammer Williams Company | Juan | Jeevan | Full | 2026-07-08 | 2026-07-14 | 2026-07-14 | 2026-08-01 | Active+Passive | FSA Plans | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2026-07-16 | Rate Changes - Medical and Vision. Reminder Email: 7/9, 7/10, 7/11 , 7/12, 7/13, 7/14
14 | 2026-06-25 | Juneau Construction Company LLC | Juan | Vamsi | Full | 2026-07-06 | 2026-07-15 | 2026-07-15 | 2026-08-01 | Active+Passive | FSA and Dependent Care FSA | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-07-20 | Rates changes - Medical Plans only. New Plan - HRA Plan, Pet Insurance Plan We have added Domestic Partner for the all the plans (Medical, Dental, Vision, Basic life Ad &D, Voluntary Life Plan, Accident, Critical illness). Reminder Emails: 7/9,7/13,7/15 - 11 am EST
15 | 2026-06-10 | McBride Building Supply | Nitya | Jeevan | Full | 2026-06-26 | 2026-07-10 | 2026-07-10 | 2026-08-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-07-13 | Rate Changes Medical, Dental Reminder Email: 7/1 , 7/6, 7/8
16 | 2026-07-01 | Precision Group | Nitya | Jeevan | Full | 2026-07-20 | 2026-08-10 | 2026-08-10 | 2026-09-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-08-12 | Rate Changes - Medical. Reminder Email: 7/22, 7/24, 7/28, 7/30, 8/4, 8/6, 8/10 Emails can go out 5am PST
17 | 2026-07-20 | Altitude Health Services LLC | Nitya | Jeevan | Full | 2026-07-27 | 2026-08-07 | 2026-08-07 | 2026-09-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2026-08-11 | Rate Changes Medical Reminder Email: 7/27, 7/31, 8/5, 8/7
18 |  | Enertia Software | Juan | Jeevan | Full |  |  |  | 2026-10-01
19 |  | Gilbert May dba Phillips May Corporation | Juan | Jeevan | Full |  |  |  | 2026-10-01
20 | 2026-08-21 | Wagner Roofing Company | Nitya | Vamsi | Full | 2026-08-30 | 2026-09-11 | 2026-09-11 | 2026-10-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team |  |  |  | Rate Changes for only Medical plans Reminder Emails:
21 |  | North American Manufacturing Corp | Nitya | Vamsi | Full |  |  |  | 2026-12-01
22 |  | 1910 Legacy Enterprises Inc. | Juan | Jeevan | Full |  |  |  | 2027-01-01
23 |  | Acme Truck Line Inc | Juan | Jeevan | Full |  |  |  | 2027-01-01
24 |  | Ahern | Nitya | Jeevan | Full |  |  |  | 2027-01-01
25 |  | ark data centers | Juan | Vamsi | Full |  |  |  | 2027-01-01
26 |  | Armstrong Technology Inc | Juan | Vamsi | Full |  |  |  | 2027-01-01
27 |  | ATK Energy Group | Juan | Jeevan | Full |  |  |  | 2027-01-01
28 |  | AXISCADES | Nitya | Jeevan | Full |  |  |  | 2027-01-01
29 |  | Brightmark | Juan | Vamsi | Full |  |  |  | 2027-01-01
30 |  | Don Hummer Trucking | Juan | Vamsi | Full |  |  |  | 2027-01-01
31 |  | Flora Food Group | Juan | Vamsi | Full |  |  |  | 2027-01-01
32 |  | Healthcare of Iowa | Nitya | Jeevan | Full |  |  |  | 2027-01-01
33 |  | Howard Sheppard LLC | Juan | Vamsi | FSA Only |  |  |  | 2027-01-01
34 |  | Johnson Real Estate Investors LLC | Juan | Jeevan | Full |  |  |  | 2027-01-01
35 |  | ORourke Sales Company | Juan | Vamsi | Full |  |  |  | 2027-01-01
36 |  | Point of Rental | Nitya | Jeevan | Full |  |  |  | 2027-01-01
37 |  | Sievert Electric | Nitya | Jeevan | Full |  |  |  | 2027-01-01
38 |  | SOAR Transport | Nitya | Vamsi | Full |  |  |  | 2027-01-01
39 |  | Thompson Concrete | Nitya | Vamsi | Full |  |  |  | 2027-01-01
40 |  | Visiting Nurse Health System | Nitya | Vamsi | Full |  |  |  | 2027-01-01
41 |  | World Class Industries Inc | Juan | Vamsi | Full |  |  |  | 2027-01-01
42 |  | Direct Traffic Control Inc | Nitya | Jeevan | Full |  |  |  | 2027-01-01
43 |  | Marcus Construction | Nitya | Vamsi | Full |  |  |  | 2027-01-01
44 |  | United Services Group | Nitya | Vamsi | Full |  |  |  | 2027-01-01
45 |  | Higdon Construction LLC | Nitya | Jeevan | Full |  |  |  | 2027-01-01
46 |  | Bryan Construction Inc | Nitya | Vamsi | Full |  |  |  | 2027-01-01
47 |  | Jakes Electric LLC | Nitya |  | Full
48 |  | Advanced Refrigeration and Air Inc | Nitya |  | Full
49 |  | ADK Electric Corporation | Nitya |  | Full
Note on L1: DilipK: Life, Voluntary AD & D, FSA - HC, FSA - DC, Critical Illness, Accident Plan, Transit, Parking, EAP, Group Hospital Indemnity, Commuter Benefits, AFLAC, Cancer, 401K, Tobacco Surcharge Plan, Spousal Surcharge Plan
Note on M1: Accident Plan, Transit, Parking, EAP, Group Hospital Indemnity, Commuter Benefits, AFLAC, Cancer, 401K, Tobacco Surcharge Plan, Spousal Surcharge Plan

## OE Tracker Jan - Dec 2025
S.No | OE Renewal Doc Receive/ Received Date | Client | CRM | Config Analyst | OE Type | Sort By OE Start Date -1 Blackout | OE End Date (EE) | OE End Date (HR) | OE Effective | Type of OE | Plans with Active OE | Plans with Passive OE | OE Setup Status | Review/Testing Status | Finalization Rules Status | Announcement Email to be Sent By | Reminder Emails Frequency | OE Closure | OE Finalization Date | HGS Comments
1 | 2025-02-11 | Barnum and Celillo Electric Inc | Nitya | Pratyush | Full | 2025-02-24 | 2025-03-19 | 2025-03-19 | 2025-04-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-03-20 | Rate changes for Medical plans. Reminder Emails -
2 | 2025-03-01 | Fiore and Sons Inc. | Juan | Pratyush | Full | 2025-03-15 | 2025-03-31 | 2025-03-31 | 2025-05-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-04-01 | Medical plan carrier changed from HealthComp to Personify (formerly HealthComp) Dental plan premium changes Vision plan rate changes Accident, Critical Illness, Hospital Indemnity rate changes HSA, FSA HC and Dependent Care carrier changed from Rocky Moutain Reserve to Lively Reminder Email Frequency - Daily
3 | 2025-04-07 | Howard Sheppard LLC | Juan | Shilpa | Full | 2025-04-28 | 2025-04-28 | 2025-05-09 | 2025-06-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-05-12 | There is rate changes for Medical and Dental Plans. Salary Uploads and Class change for 9 employees completed eff 6/1. Reminder Emails are 04/30, 05/02, 05/04, 05/06, 05/08 and 05/09
4 | 2025-04-23 | Metalpros LLC | Nitya | Pratyush | Full | 2025-05-01 | 2025-05-15 | 2025-05-15 | 2025-06-01 | Active | All Plans | Basic Life LTD | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-05-16 | Medical, Dental, LTD plan rate changes Reminder Emails - May 10, May12, May 13, May 14
5 | 2025-05-13 | Evans Contracting Group | Jasmin | Pratyush | Full | 2025-05-16 | 2025-05-23 | 5/23/20250 | 2025-06-01 | Active | All Plans | N/A | Completed | Completed |  | Client | Not Required | Completed | 2025-05-26 | Medical, Dental and Vision plans are there for this new client
6 | 2025-06-03 | TetraMem | Juan | Pratyush | Medical | 2025-05-22 | 2025-05-29 | 2025-05-29 | 2025-06-01 | Passive | N/A | All Plans | Completed | Completed | Received | Client | Not Required | Completed | 2025-05-29 | There's no need to set up an Open Enrollment in the system at this time, as HR is collecting changes from employees via paper forms. We have added new set of Medical plans because of rate structure changes. We have added two new classes - “All Benefit-Eligible Employees” “All Highly Compensated Benefit-Eligible Employees"
7 | 2025-05-21 | HealthCare Access Maryland Inc | Nitya | Pratyush | Full | 2025-06-02 | 2025-06-13 | 2025-06-13 | 2025-07-01 | Passive | FSA Plan | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-06-16 | Medical plan rate changes Reminder emails: reminders on the 2nd, 9th, and 12th!
8 | 2025-04-18 | Iowa City Community School District | Juan | Shilpa | Full | 2025-05-01 | 2025-05-31 | 2025-05-31 | 2025-07-01 | Active+Passive | FSA Plan | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-06-02 | No changes in OE. Reminder Email Frequency - Every Other Day
9 | 2025-07-01 | Hammer Williams Company | Juan | Shilpa | Full | 2025-07-14 | 2025-07-18 | 2025-07-18 | 2025-08-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-07-21 | New Medical plans added and mapping is as per below. $5000 to $5100 $2500 to $2600 $1500 to $1600 Rate changes for Medical and Buy Up plan. Reminder Emails - 7/15,7/16,7/17,7/18
10 | 2025-06-20 | Juneau Construction Company LLC | Jasmin | Pratyush | Full | 2025-07-03 | 2025-07-13 | 2025-07-13 | 2025-08-01 | Active+Passive | All Plans | Basic Life LTD STD | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-07-14 | Rate changes for Medical. Carrier changed for Dental, Basic Life, STD, LTD, Vol Life, Accident and Critical Illness to Lincoln Financial Group from UNUM Reminder email - 7/4, 7/7, 7/9, 7/11
11 | 2025-07-29 | Altitude Health Services LLC | Nitya | Pratyush | Full | 2025-08-04 | 2025-08-15 | 2025-08-15 | 2025-09-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-08-18 | Rate changes for Medical, Dental and Vision plans. HSA carrier changed from Further to Health Equity. Since we cannot add two HSA plans we have changed the carrier in the current plan. Reminder Email is Every 4 days
12 | 2025-08-05 | Pak-Lite Inc | Juan | Pratyush | Full | 2025-08-18 | 2025-08-25 | 2025-08-25 | 2025-09-01 | Active+Passive | All Plans | Basic Life LTD EAP | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-08-26 | Carrier changed for Dental, Vision, Basic Life, STD, LTD, Vol Life, Critical Illness, Accident, Hospital Indemnity to Lincoln Financial. Medical plan rate changed.
13 | 2025-09-05 | Enertia Software | Juan | Jeevan S | Full | 2025-09-18 | 2025-09-25 | 2025-09-25 | 2025-10-01 | Active+Passive | FSA HC and FSA DC | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-09-26 | 1) Added one Dental plan with new carrier The Standard. 2) Added new two medical plan ($6,000 HDHP Base Plan, $0 SimplePlan Tiered Mid-Plan), 3) Updated rate changes for - Medical($1,000 PPO Buy-Up Plan) 4) Plans Terminating: Dental PPO $5,000 HDHP Base Plan $2,000 PPO Mid-Plan
14 | 2025-09-10 | Gilbert May dba Phillips May Corporation | Jasmin | Kiran | Full | 2025-09-15 | 2025-09-19 | 2025-09-19 | 2025-10-01 | Passive | NA | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-09-22 | We have Added new Plan New BCBS Dental Plan, BCBS Voluntary Vision,BCBS Basic Life and AD&D, BCBS Short-Term Disability,BCBS Long-Term Disability,BCBS Voluntary Life and AD&D. Medical Plan Plan 1 With Wellness - HMO MTBEE044 to Plan 1 With Wellness - HMO MTBEE544, and Plan 1 Non-Wellness - HMO MTBEE044 to Plan 1 Non-Wellness - HMO MTBEE544
15 | 2025-11-25 | 1910 Legacy Enterprises Inc. | Juan | Shilpa | Full | 2025-12-04 | 2025-12-10 | 2025-12-10 | 2026-01-01 | Passive | NA | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-11 | Rate changes for Medical Plan. Reminder Emails - 12/6, 12/8, 12/9, 12/10
16 | 2025-10-30 | Acme Truck Line Inc | Juan | Jeevan S | Full | 2025-11-10 | 2025-11-21 | 2025-11-26 | 2026-01-01 | Active+Passive | MDV and HAS | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-04 | Medical, Dental Rate changed. New Information only plan "HealthJoy" is added. Enrollment based on Medical.
17 | 2025-10-09 | Ahern | Nitya | Jeevan S | Full | 2025-11-12 | 2025-11-21 | 2025-11-21 | 2026-01-01 | Active+Passive | Medical Dental Vision FSA Critical Illness PTO Buy Up Accident Hospital Indemnity | Basic Life Additional Benefits ID Theft | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-11-24 | 1) Rate changes for Medical and Dental. 2) Updated the Maximum Annual limits for FSA Dependent Care. 3) Updated the HSA contribution limit for 2026. Reminder Emails - (11/17 - 11/21) 8 am CT
18 | 2025-10-28 | ark data centers | Juan | Shilpa | Full | 2025-11-10 | 2025-11-21 | 2025-11-21 | 2026-01-01 | Active+Passive | Medical | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-11-24 | New Medical Plans Added and mapping is as per below. $3400 to TBD $1000 to TBD $5000 to TBD Rate changes for Dental Plan. Reminder Emails - 11/12,11/14,11/16,11/18,11/20,11/21
19 | 2025-11-11 | Armstrong Technology Inc | Juan | Vamsi | Full | 2025-11-13 | 2025-12-05 | 2025-12-05 | 2026-01-01 | Active+Passive | All Plans | All Plans | Completed | Completed | Received | Client | Not Required | Completed | 2025-12-10 | Rate changes for Medical plans only
20 | 2025-11-26 | ATK Group | Jasmin | Shilpa | Full | 2025-12-08 | 2025-12-15 | 2025-12-19 | 2026-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-22 | Rate changes for Medical, Dental, Vision plans. Medical - Silver plan is ending, any EE who is enrolled in Silver plan currently will be moved to Gold plan (if they don’t login in OE) Reminder Emails - December 09, December 11, December 15
21 | 2025-12-05 | AXISCADES | Nitya | Jeevan S | Full | 2025-12-15 | 2025-12-19 | 2025-12-19 | 2026-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-22 | 1. Rate changes for Medical($3,200 Deductible Base HSA), Dental and Vision. 2. Carrier Changes for Basic Life, Voluntary Life, Voluntary STD, Voluntary LTD, EAP, Travel Assistance and Will Prep. 3. ASPCA Pet Insurance, Voluntary Hospital Indemnity, Voluntary Critical Illness, Voluntary Accident are newly added plans. Reminder Frequency - 12/17 and 12/19
22 | 2025-10-09 | Brightmark | Juan | Vamsi | Full | 2025-10-22 | 2025-11-05 | 2025-11-05 | 2026-01-01 | Active+Passive | FSA HC and FSA DC | All Plans | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2025-11-06 | 1) New plan added - Blue Shield of CA HDHP PPO $1700 2) Rate Changes for medical and paid family Leave. Blue Shield of CA LD PPO $500 Blue Shield of CA Value Plan PPO $2000 Kaiser HMO $20 Plan Limits updated to 2026 for HSA Parking Transit and Fsa Reminder Frequency - 10/29, 11/5
23 | 2025-11-12 | Don Hummer Trucking | Jasmin | Vamsi | Full | 2025-11-24 | 2025-12-05 | 2025-12-05 | 2026-01-01 | Passive | All Plans | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-08 | Medical, Dental, Vision plans are carrier changing, rate changes, plan changes.Group Accident plan is changing rate and Health joy is new plan. Reminder Emails are: 11/26, 11/28, 11/30, 12/02, 12/04, 12/05.
24 | 2025-10-22 | Flora Food Group | Juan | Shilpa | Full | 2025-11-02 | 2025-11-16 | 2025-11-16 | 2026-01-01 | Active+Passive | FSA HC and FSA DC | All Plans | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2025-11-17 | There is rate changes for Medical and Dental Plans. Reminder Emails are 11/9 and 11/16
25 | 2025-10-28 | Healthcare of Iowa | Nitya | Jeevan S | Full | 2025-11-17 | 2025-11-28 | 2025-11-28 | 2026-01-01 | Active+Passive | FSA HC and FSA DC | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-01 | Refer to the teamwork link with our comments on the plan changes for Medical. https://appriver3651007094.sharepoint.com/:x:/g/Eca8nHP1OTRJp2SX7Xk55tkBTQf513XbQv_-aIICJmN4mg?e=TnReyz
26 | 2025-10-16 | Howard Sheppard LLC | Juan | Vamsi | FSA Only | 2025-11-03 | 2025-11-28 | 2025-11-28 | 2026-01-01 | Active |  | N/A | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-01 | Reminder Emails are Monday, Wednesday and Friday of each week. Daily November 24-28
27 | 2025-10-31 | Johnson Real Estate Investors LLC | Juan | Jeevan S | Full | 2025-11-14 | 2025-12-01 | 2025-12-02 | 2026-01-01 | Active+Passive | All Plans | N/A | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-03 | There is rate changes for Medical, Dental Reminder Emails on 11/19, 11/26 and 11/30
28 | 2025-11-13 | ORourke Sales Company | Jasmin | Vamsi | Full | 2025-11-24 | 2025-12-05 | 2025-12-05 | 2026-01-01 | Active+Passive | All Plans |  | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-08 | There is rate changes for all Medical plans and Dental Remainder Emails are: 11/26,11/29,12/01,12/03,12/05
29 | 2025-11-13 | Point of Rental | Nitya | Jeevan S | Full | 2025-11-17 | 2025-11-21 | 2025-11-21 | 2026-01-01 | Active+Passive | FSA HC and FSA DC | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-11-24 | There is rate changes for Medical, Dental, Voluntary Life, Vision, Basic Life and Long-Term Disability
30 | 2025-12-05 | Sievert Electric | Nitya | Shilpa | Full | 2025-12-15 | 2025-12-19 | 2026-01-01 | 2026-01-01 | Active+Passive |  | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-12-23 | Medical plan carrier changes to UHC from BCBS of IL Reminder Frequency - 12/16,12/17,12/18,12/19
31 | 2025-12-11 | SOAR Transport | Nitya | Vamsi | Full | 2025-12-16 | 2025-12-18 | 2025-12-23 | 2026-01-01 | Active+Passive | FSA HC and FSA DC | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2025-12-24 | Medical Plan Carrier changes to BCBS of Tennessee. Reminder email - 12/17,12/18,12/19,12/20,12/21,12/22,12/23
32 | 2025-10-31 | Thompson Concrete | Nitya | Vamsi | Full | 2025-11-09 | 2025-11-21 | 2025-11-21 | 2026-01-01 | Active+Passive | All Plans | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-11-24 | Medical plans only changing rates Reminder Emails are: 11/12,11/19,11/21 at 5am PST
33 | 2025-11-07 | Visiting Nurse Health System | Nitya | Pratyush | Full | 2025-11-14 | 2025-12-03 | 2025-12-03 | 2026-01-01 | Active+Passive | HAS, FSA, Vol Life | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-04 | New Cigna Medical plan along with the current EBS medical plans are offered to employee from OE. Rate changes for Basic Life, STD, LTD, Vol Life, Accident, Critical Illness and Hospital Indemnity. Carrier change for Vision from Vision Service Plan to MetLife New plans Identity Theft and Pet Insurance from MetLife and EAP plan from Curalinc are being offered Reminder emails - Every Other Day
34 | 2025-10-29 | World Class Industries Inc | Juan | Vamsi | Full | 2025-11-10 | 2025-11-21 | 2025-11-21 | 2026-01-01 | Active+Passive | FSA HC and FSA DC | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-11-24 | Medical,Dental,Vision plans are rate changing and Pet Insurance is New Plan Reminder Emails are 11/10,11/12,11/14,11/16,11/18,11/20,11/21
35 | 2025-08-29 | Wagner Roofing Company | Nitya | Shilpa | Full | 2025-09-04 | 2025-09-12 | 2025-09-12 | 2025-10-01 | Active | All Plans | N/A | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-09-15 | Reminder Emails are 09/09,09/11 and 09/12
36 | 2025-10-28 | Direct Traffic Control Inc | Nitya | Pratyush | Full | 2025-11-03 | 2025-11-10 | 2025-11-10 | 2026-01-01 | Active+Passive | FSA HC, FSA DC and HSA | All Plans | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2025-11-11 | Medical, Dental Rate changes. Carrier changed to Flores for FSA and HSA plans
37 | 2025-12-09 | NS Giles | Nitya | Pratyush | Full | - | - | - | 2025-12-01 | Passive | N/A | All Plans | Completed | Completed | Received | - | Not Required | Completed | 2025-12-09 | This was an offine OE. OE enrollments provided in PDFs files and others were rolled over.
38 | 2025-11-10 | Marcus Construction | Nitya | Vamsi | Full | 2025-11-13 | 2025-12-02 | 2025-12-02 | 2026-01-01 | Active+Passive | All Plans | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-10 | Rate changes for Medical,Dental,Basic Life and AD&D,Voluntary Short-Term Disability,Voluntary LTD Remainder Emails are 11/15,11/17,11/19,11/21,11/23,11/25,11/26
39 | 2025-11-20 | Odyssey Manufacturing Co | Nitya | Pratyush | Full | 2025-11-24 | 2025-12-05 | 2025-12-05 | 2026-01-01 | Active+Passive | FSA | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-15 | Rate changes for Medical, Dental, Basic Life, Vol STD and Vol LTD. Reminder email frequency - Dec 1st and 4th. Daily reminders from 12/8,12/9,12/10,12/11,12/12.
40 |  | United Services Group | Nitya | Vamsi | Full |  |  |  | 2026-01-01
41 | 2025-11-27 | Mangieri Electric | Jasmin | Shilpa | Full | 2025-12-02 | 2025-12-12 | 2025-12-12 | 2026-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2025-12-15 | This is Medical Plan OE Reminders - 12/4,12/6,12/8,12/10,12/12
42 | 2025-12-11 | Higdon Construction | Jasmin | Shilpa | Full | 2025-12-16 | 2025-12-22 | 2025-12-22 | 2026-01-01 | Passive | N/A | All Plans | Completed | Completed |  | Configuration Team | On Particular Dates | Completed | 2025-12-30 | This is going live with OE with a medical plan and HSA. Reminder Email 17,19,21 and 22
Note on L1: DilipK: Life, Voluntary AD & D, FSA - HC, FSA - DC, Critical Illness, Accident Plan, Transit, Parking, EAP, Group Hospital Indemnity, Commuter Benefits, AFLAC, Cancer, 401K, Tobacco Surcharge Plan, Spousal Surcharge Plan
Note on M1: Accident Plan, Transit, Parking, EAP, Group Hospital Indemnity, Commuter Benefits, AFLAC, Cancer, 401K, Tobacco Surcharge Plan, Spousal Surcharge Plan

## OE Tracker Jan - Dec 2024
S.No | OE Renewal Doc Receive/ Received Date | Client | CRM | Config Analyst | OE Type | Sort By OE Start Date -1 Blackout | OE End Date (EE) | OE End Date (HR) | OE Effective | Type of OE | Plans with Active OE | Plans with Passive OE | OE Setup Status | Review/Testing Status | Finalization Rules Status | Announcement Email to be Sent By | Reminder Emails Frequency | OE Closure | OE Finalization Date | HGS Comments
1 | 2024-01-03 | Brookfield Enterprise | Janice | Nischith | Full | 2024-01-03 | 2024-01-23 | 2024-01-23 | 2024-02-01 | Active | All Plans | N/A | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-01-24 | Reminder Emails - 1/12,1/13,1/14,1/15,1/16 and 1/17
2 | 2024-02-14 | Barnum and Celillo Electric Inc | Nitya | Pratyush | Full | 2024-02-19 | 2024-03-15 | 2024-03-15 | 2024-04-01 | Passive | N/A | All Others | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-03-16 | Rate changes for Medical and Dental. Reminder Email frequency - once per week until March 15th
3 | 2024-02-02 | Lulazon Logistics LLC. | Janice | Rakshith | Full | 2024-02-13 | 2024-03-26 | 2024-03-26 | 2024-04-01 | Active | Medical, Dental, Vision, Accident, Critical Illness, Hospital Indemnity | Basic Life | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-03-27 | Reminder Emails -2/15,2/16,2/19 and 2/20
4 | 2024-02-26 | Fiore and Sons Inc. | Juan | Rakshith | Full | 2024-03-09 | 2024-03-22 | 2024-03-22 | 2024-05-01 | Active | Medical | All Others | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-03-25 | Career Changes for Medical plan Cancer plan Has been Terminated Reminder email Frequency - Daily untill March 22
5 | 2024-03-29 | Lead The Way Logistics | Janice | Nischith | Full | 2024-04-06 | 2024-04-18 | 2024-04-18 | 2024-05-01 | Active | All Plans | N/A | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-04-19 | Reminder Emails - 04/8, 4/10, 04/12, 4/15, 04/16 and 04/17
6 | 2024-04-24 | Point of Rental | Nitya | Nischith | FSA | 2024-04-25 | 2024-04-30 | 2024-04-30 | 2024-05-01 | Active | FSA Plans | N/A | Completed | Completed | Received | Client | Not Required | Completed | 2024-05-02 | This is FSA Plan OE
7 | 2024-04-11 | Point of Rental (Record 360) | Nitya | Pratyush | Full | 2024-04-15 | 2024-04-22 | 2024-04-22 | 2024-05-01 | Active | All Others | Basic Life, LTD | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-04-23 | This OE is for the Record 360 location employees. Newly added FSA HC and DC plans but they are not part of this OE. New Medical PPO $500 is offered for the employees in this location. Medical deductions are different for this group for the exisiting plans. Reminder Emails - 04/16, 4/17, 04/18, 4/19, 04/20 04/21 and 04/22
8 | 2024-05-03 | Castles Technology | Jasmin | Nischith | Full | 2024-05-13 | 2024-05-22 | 2024-05-22 | 2024-06-01 | Active+Passive | FSA Plans | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-05-23 | We willl receive salary file on 05/06/2024. We will need to upload salary file during blackout. There is no rate changes to the plan. We need to add Voluntary Benefits Information Plan. Reminder Emails are 05/14,05/16,05/18,05/20,05/22
9 | 2024-04-03 | Howard Sheppard LLC | Juan | Nischith | Full | 2024-04-15 | 2024-05-03 | 2024-05-03 | 2024-06-01 | Passive | N/A | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-05-06 | There is rate changes for Medical and Dental Plan. There is salary upload in the blackout. Reminder Emails 04/16,04/18, 04/20, 04/22, 04/24, 04/26, 04/28, 04/30, 05/02, 05/03
10 | 2024-04-30 | TetraMem | Juan | Shilpa | Medical and FSA | 2024-05-10 | 2024-05-22 | 2024-05-22 | 2024-06-01 | Active+Passive | FSA Plans | Medical | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-05-23 | Rate changes for Medical Plans, We have added the FSA HC and Dependent care palns with Carrier WEX. There is Medical Plan Termination Kaiser Silver 70 Deductible HMO 2800/65 + Child Dental ALT Plan and Kaiser Silver 70 HDHP HMO 2700/25% + Child Dental Plan (GF3). Reminder Emails are 05/11,05/13,05/15,05/17,05/19,05/20
11 | 2024-04-05 | City of Clive | Juan | Nischith | Full | 2024-04-29 | 2024-05-10 | 2024-05-10 | 2024-07-01 | Active+Passive | Medical, Dental, Vision, LTD Premium Taxation, Custom Medical | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-05-13 | There are rate changes for Medical, Dental and Custom Medical Plans. Reminder Emails is 04/30, 05/02, 05/04, 05/06, 05/08 and 05/10. There is Medical plan and Custom Medical Plan is terminating
12 | 2024-05-22 | HealthCare Access Maryland Inc | Nitya | Pratyush | Full | 2024-06-03 | 2024-06-14 | 2024-06-14 | 2024-07-01 | Active+Passive | FSA Plans | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-06-18 | Medical plan rate changes. Reminder emails every other day and daily last 3 days
13 | 2024-04-23 | Iowa City Community School District | Juan | Nischith | Full | 2024-05-06 | 2024-05-31 | 2024-05-31 | 2024-07-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-06-03 | There is rate change for Medical, and Vision Plan. Reminder Emails are May 6th, 9th, 13th and 16th. Daily beginning May 20
14 | 2024-06-11 | Hammer Williams Company | Juan | Gnanavelu | Full | 2024-06-24 | 2024-07-09 | 2024-07-09 | 2024-08-01 | Active+Passive | FSA Plans | All Others | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-07-10 | Medical, Dental and Vision Plans Rates changed. Reminder Emails are 07/01, 07/08
15 | 2024-06-08 | Juneau Construction Company LLC | Jasmin | Nischith | Full | 2024-06-24 | 2024-07-03 | 2024-07-03 | 2024-08-01 | Active+Passive | FSA Plans | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-07-04 | Medical plan rate changes. Reminder emails on - 6/26, 6/28, 7/1, 7/3
16 | 2024-07-12 | Altitude Health Services LLC | Nitya | Nischith | Full | 2024-07-22 | 2024-08-02 | 2024-08-02 | 2024-09-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-08-05 | 2024-07-29
17 | 2024-08-02 | Pak-Lite Inc | Juan | Pratyush | Full | 2024-08-16 | 2024-08-23 | 2024-08-23 | 2024-09-01 | Active+Passive | All Others | Basic Life, ER paid LTD, EAP | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-08-26 | Medical Plan Carrier Changed UHC to Aetna, Class based Annoucement Email need to send. No changes for all other plans. Reminder Frequency: Every other day
18 | 2024-09-04 | Enertia Software | Juan | Nischith | Full | 2024-09-13 | 2024-09-20 | 2024-09-20 | 2024-10-01 | Active+Passive | FSA Plans | All Others | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-09-23 | There is Carrier Change for Medical Plan from BCBS of Texas to Cigna. There is rate changes for Medical, Dental and Vision Plan. Reminder Emails are 09/14, 09/15, 09/16, 09/17, 09/18, 09/19 and 09/20
19 | 2024-09-09 | Gilbert May dba Phillips May Corporation | Jasmin | Shilpa | Full | 2024-09-16 | 2024-09-26 | 2024-09-26 | 2024-10-01 | Passive | N/A | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-09-27 | There is rate change for Medical and Dental Plan
20 | 2024-09-14 | Armstrong Technology Inc | Juan | Nischith | Full | 2024-09-30 | 2024-10-11 | 2024-10-11 | 2024-11-01 | Passive | N/A | All Others | Completed | Completed | Received | Client | Not Required | Completed | 2024-11-05 | Rate changes in Medical Armstrong Tech SV Kaiser plan only.
21 | 2024-11-19 | 1910 Legacy Enterprises Inc. | Juan | Pratyush | Full | 2024-12-02 | 2024-12-10 | 2024-12-10 | 2025-01-01 | Active+Passive | FSA Plans | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-11 | Carrier changes for Dental, Basic Life, STD, LTD and Vol Life Medical plan rate changes Reminder emails - 12/4, 12/6, 12/9, 12/10
22 | 2024-10-30 | ABCM | Juan | Pratyush | Full | 2024-11-12 | 2024-11-26 | 2024-11-26 | 2025-01-01 | Passive | N/A | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-11-27 | Rate changes for Medical and Vision. Reminder Emails are 11/14, 11/16, 11/18, 11/20, 11/22 and 11/23
23 | 2024-10-25 | Acme Truck Line Inc | Juan | Pratyush | Full | 2024-11-11 | 2024-11-22 | 2024-11-29 | 2025-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-02 | Carrier changed from Voya to MOO for Critical Illness, Accident, ER Paid CI and HI plans Reminder Email - Nov. 12, 14, 18, 20, 22 Finalization rules are provided - https://wfj.teamwork.com/#/messages/1216069?pmp=4250586
24 | 2024-10-22 | Ahern | Nitya | Shilpa | Full | 2024-11-13 | 2024-11-22 | 2024-11-22 | 2025-01-01 | Active+Passive | All Others | Basic Life, LTD | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-11-25 | There are no changes. Reminder Emails:11/18,11/19, 11/20, 11/21, 11/22 Salary Changes, Location Changes effective 1/1/2025 Job Title changes effective 11/1/2024 Department changes effective 1/1/2025 Email Id updates effective 1/1/2025
25 | 2024-11-09 | ark data centers | Juan | Pratyush | Full | 2024-11-21 | 2024-12-06 | 2024-12-06 | 2025-01-01 | Active+Passive | Medical, Dental, Vision, HSA Account Set Up | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-09 | Carrier changes for Dental, Vision, Basic Life, STD, LTD, Vol Life and Employee Assistance Program New plan Vol Cancer has been added with prosperity carrier. The STD and LTD plans are split based on class. For the Regular Full Time Officer class we have Executive STD and LTD plans and the other plan for the remaning classes. Reminder email - Every other day
26 | 2024-11-07 | Armstrong Technology Inc | Juan | Shilpa | Full | 2024-11-08 | 2024-11-27 | 2024-11-27 | 2025-01-01 | Active+Passive | Medical | All Others | Completed | Completed | Received | Client | Not Required | Completed | 2024-12-04 | There is new carrier added for Medical Plan
27 | 2024-12-05 | AXISCADES | Nitya | Pratyush | Full | 2024-12-16 | 2024-12-23 | 2024-12-23 | 2025-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-12-24 | Medical plan carrier changed to Cigna Dental Rate changes
28 | 2024-09-25 | Brightmark | Juan | Gnanavelu | Full | 2024-10-22 | 2024-11-05 | 2024-11-08 | 2025-01-01 | Active+Passive | FSA Healthcare and Limited Care | All Others | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-11-11 | Medical, Dental and Vision plans rates changes, Carrier changed for STD and LTD New The NYDBL / PFL plan added Annual contibution for 2025 and ER contributions updated for HSA Plan updated Annual IRS limit updated for FSA Health and Limited FSA plan Commuter contribution updated to $325 from $315 for 2025 No Changes for Basic and Voluntary Life and Critical illness plans
29 | 2024-10-29 | C. Mondavi and Family | Nitya | Shilpa | Full | 2024-11-11 | 2024-11-29 | 2024-11-29 | 2025-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Client | Not Required | Completed | 2024-12-02 | Rate changes for Medical and Dental New Dental Plan added - United Concordia Dental Enhanced
30 | 2024-10-21 | CEC | Juan | Pratyush | Full | 2024-11-11 | 2024-11-20 | 2024-11-22 | 2025-01-01 | Active+Passive | FSA Plans | All Others | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-11-21 | No Carrier change or rate changes this time
31 | 2024-11-04 | Don Hummer Trucking | Jasmin | Shilpa | Full | 2024-11-25 | 2024-12-06 | 2024-12-06 | 2025-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-09 | Rate changes for Medical Plans Reminder - 11/27,11/29,12/1,12/3,12/5
32 | 2024-11-03 | Flora Food Group | Juan | Pratyush | Full | 2024-11-18 | 2024-12-01 | 2024-12-01 | 2025-01-01 | Active+Passive | FSA Healthcare and Limited Care | All Others | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-12-02 | There is Carrier Change for Medical, Dental and Vision Plan from Aetna to Cigna. New Health Advocate plan is added. Reminder email on 11/25 and 12/1
33 | 2024-11-02 | Fort Madison and Montrose | Nitya | Shilpa | Full | 2024-11-18 | 2024-11-29 | 2024-11-29 | 2025-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-02 | Reminder emails on 11/25 and 11/29
34 | 2024-11-18 | Healthcare of Iowa | Nitya | Shilpa | Full | 2024-12-02 | 2024-12-09 | 2024-12-09 | 2025-01-01 | Active+Passive | FSA Plans | All Plans | Completed | Completed | Received | Client | Not Required | Completed | 2024-12-11 | Refer to the teamwork link with our comments on the plan changes for Medical. https://wfj.teamwork.com/app/projects/500220/messages.
35 | 2024-10-17 | Howard Sheppard LLC | Juan | Shilpa | FSA Only | 2024-11-01 | 2024-11-29 | 2024-11-29 | 2025-01-01 | Active | FSA Plans | N/A | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-12-02 | This is FSA Plan OE Reminder Email are 11/8, 11/15, 11/22 and 11/29
37 | 2024-11-02 | Interior Investments LLC | Juan | Shilpa | Full | 2024-11-18 | 2024-11-26 | 2024-11-26 | 2025-01-01 | Active+Passive | Medical, Dental, Vision and FSA Plans | All Others | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-11-27 | Reminder Emails are 11/19,11/20,11/21,11/22,11/23,11/24,11/25 and 11/26
38 | 2024-11-04 | Johnson Real Estate Investors LLC | Juan | Gnanavelu | Full | 2024-11-18 | 2024-12-04 | 2024-12-04 | 2025-01-01 | Active | All Plans | N/A | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-05 | Medical and Dental carrier changed to CIGNA Healthcare Reminder Emails on 11/25, 12/3/2024 and 12/4/2024
40 | 2024-11-18 | Mid-Iowa Co-op | Jasmin | Shilpa | Full | 2024-11-22 | 2024-12-06 | 2024-12-06 | 2025-01-01 | Active+Passive | All Plans | Basic Life | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-12-09 | Medical - All new plans added and the existing will be terminated. Dental rates changed. Reminder email on 11/23 to 12/6
41 | 2024-11-18 | Mid Iowa Milling | Jasmin | Shilpa | Full | 2024-11-22 | 2024-12-06 | 2024-12-06 | 2025-01-01 | Active | All Plans | N/A | Completed | Completed |  | Configuration Team | Daily | Completed | 2024-12-09 | New Client, New Employees. Only Demographics loaded Reminder email on 11/23 to 12/6
42 | 2024-11-12 | SOAR Transport | Nitya | Shilpa | Full | 2024-11-20 | 2024-11-27 | 2024-11-27 | 2025-01-01 | Active+Passive | Medical | All Others | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-11-28 | New Medical plans added PPO and HDHP with the carrier Aetna. Old Medical plans with carrier BCBS of Tenessee to be deleted Rate changes for Dental plans Reminder email from 11/23 to 12/6
44 | 2024-11-13 | ORourke Sales Company | Jasmin | Pratyush | Full | 2024-11-25 | 2024-12-04 | 2024-12-04 | 2025-01-01 | Active+Passive | FSA Dependent Care | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-05 | Carrier changes for Medical, Dental, Vision, Basic Life, LTD, Vol Life and Vol STD from UHC to Aetna Reminder emails - Every other day | They have an issue with Benefits Junction during open enrollment. The system does not tell you if there is an overage dependent prior to the date the child becomes overage. This causes issues on their carrier invoices as they pay in advance. At the close of OE run a dependent report and see if any dependent is going to turn 26 in December or January.
45 | 2024-12-05 | Point of Rental | Nitya | Shilpa | Full | 2024-12-11 | 2024-12-19 | 2024-12-19 | 2025-01-01 | Active+Passive | All Plans | All Others | Completed | Completed | Received | Configuration Team | Daily | Completed | 2024-12-20 | There is rate changes for Medical and Dental Plans. Medical PPO 500 Plan is terminating.
46 | 2024-11-27 | Sievert Electric | Jasmin | Shilpa | Full | 2024-12-05 | 2024-12-12 | 2024-12-12 | 2025-01-01 | Passive | N/A | All Plans | Completed | Completed | Received | Configuration Team | Weekly | Completed | 2024-12-13 | Reminder Emails is 12/12
47 | 2024-11-06 | Thompson Concrete | Jasmin | Shilpa | Full | 2024-11-08 | 2024-11-22 | 2024-11-22 | 2025-01-01 | Active | Medical,Dental,Vision, HSA, Vol Life and Vol LTD | All Others | Completed | Completed | Received | Client | Not Required | Completed | 2024-11-25 | There is rate changes for Medical,Dental and Vision
48 | 2024-11-18 | Visiting Nurse Health System | Nitya | Pratyush | Full | 2024-11-25 | 2024-12-08 | 2024-12-08 | 2025-01-01 | Passive | All Plans | N/A | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-12-09 | Carrier changed for Medical from Aetna-Allied to EBMS Carrier changed for Dental from Delta Dental to MetLife Reminder email - 11/27, 11/29, 12/4, 12/6
49 | 2024-11-02 | World Class Industries Inc | Juan | Shilpa | Full | 2024-11-12 | 2024-11-22 | 2024-11-22 | 2025-01-01 | Active+Passive | FSA Healthcare and Limited Care | All Others | Completed | Completed | Received | Configuration Team | On Particular Dates | Completed | 2024-11-25 | Reminder Emails are 11/14, 11/16 11/18, 11/20 and 11/22
50 | 2024-11-27 | ATK Group (OneSource Restoration LLC) | Jasmin | Shilpa | Full | 2024-12-04 | 2024-12-16 | 2024-12-16 | 2025-01-01 | Active | All Plans | N/A | Completed | Completed | Pending | Configuration Team | On Particular Dates | Completed | 2024-12-17 | There is medical, dental, vision and voluntary life plan
51 | 2024-12-16 | TetraMem | Juan | Shilpa | FSA Only | 2024-12-02 | 2024-12-13 | 2024-12-13 | 2025-01-01 | Active | FSA Plans | N/A | Completed | Completed | Received | Client | Not Required | Completed | 2024-12-16 | This is a FSA Only OE
Note on L1: DilipK: Life, Voluntary AD & D, FSA - HC, FSA - DC, Critical Illness, Accident Plan, Transit, Parking, EAP, Group Hospital Indemnity, Commuter Benefits, AFLAC, Cancer, 401K, Tobacco Surcharge Plan, Spousal Surcharge Plan
Note on M1: Accident Plan, Transit, Parking, EAP, Group Hospital Indemnity, Commuter Benefits, AFLAC, Cancer, 401K, Tobacco Surcharge Plan, Spousal Surcharge Plan